## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US001 | As an Admin,I want to register suppliers so that supplier information can be maintained | MUST HAVE | None | Varnika devi | 3- Completed
1 | 1 | US002 | As an Admin,I want to manage employee details so that employees can access the system | MUST HAVE | None | Imdad | 3- Completed
2 | 2 | US003 | As an Admin,I want to verify supplier compliance documents before approval | MUST HAVE | Supplier registration | Varnika devi | 3- Completed
2 | 2 | US004 | As a manager,I want to configure approval hierarchy for purchase requests | MUST HAVE | Employee Details | Imdad | 3- Completed
3 | 3 | US005 | As an Employee,I want to create purchase requests for required items | MUST HAVE | Approval Hierachy | Imdad | 3- Completed
3 | 3 | US006 | As a Procurement Officer,I want to generate purchase orders from approved requests | MUST HAVE | Purchase Request | Imdad | 3- Completed
3 | 3 | US007 | As an admin.I want to track supplier performance based on ratings and reviews | SHOULD HAVE | Supplier registration | Varnika devi | 3- Completed
4 | 4 | US008 | As a Finance Officer,I want to process payments after goods receipt confirmation | MUST HAVE | Purchase Request | Imdad | 3- Completed
4 | 4 | US009 | As a manager,I want to view procurement reports and dashboards | COULD HAVE | All modules | Varnika devi | 3- Completed
4 | 4 | US010 | As an admin,I want to monitor the complete procurement workflow | SHOULD HAVE | All modules | Imdad | 3- Completed
4 | 4 | US011 | As an admin, I want to implement role-based security controls so that users can access only | MUST HAVE | Employee Details | Varnika devi | 3- Completed
4 | 4 | US012 | I want to configure audit logging & monitoring so that system activities can be tracked | MUST HAVE | All modules | Imdad | 3- Completed
4 | 4 | US013 | Procurement officer,I want to integrate rest api so communicate with each other | MUST HAVE | All modules | Varnika devi | 3- Completed
4 | 4 | US014 | I want to deploy and test procurement system so that it is ready for enterprise use | MUST HAVE | Api integration | Imdad | 3- Completed
4 | 4 | US015 | I want to optimize the system performance so that application responds efficiently | SHOULD HAVE | Deployment | Varnika devi | 3- Completed
4 | 4 | US016 | I want to create comprehensive project documentation so system can be understood | SHOULD HAVE | All modules | Varnika devi | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint | Day 1 | Supplier Registration validation errors not working correctly | Reviewed validation logic and fixed input checks
Sprint 1 | Day 2 | Duplicate GST validation issue | Added duplicate GST verification in service layer
Sprint 1 | Day 3 | Supplier document upload failure | Corrected file upload configuration and tested functionality
Sprint 2 | Day 1 | Approval hierarchy mapping issue | Fixed department and approval level mappping
Sprint 2 | Day 2 | Supplier performance rating accepted invalid values | Added rating range validation(1-5)
Sprint 2 | Day 3 | Employee registration accepted duplicate email IDs | Implemented unique email validation
Sprint 3 | Day 1 | Purchase Order created without approved requisition | Added approval status validation before PO creation
Sprint 3 | Day 2 | Duplicate Purchase Orders generated | Added duplicate Po existence check
Sprint 3 | Day 3 | Inactive suppliers displayed in approved supplier list | Applied ACTIVE status filter in supplier search
Sprint 4 | Day 1 | Role-based security access issue | Added role-based access validation
Sprint 4 | Day 2 | Audit logging not capturing all user activities | Fixed audit logging and activity tracking
Sprint 4 | Day 3 | REST API integration issue between modules | Tested and fixed API integration
Sprint 4 | Day 4 | Deployment configuration issue | Corrected deployment configuration and tested the application
Sprint 4 | Day 5 | Application response time was slow | Optimized queries and improved performance
Sprint 4 | Day 6 | Project documentation was incomplete | Updated technical and user documentation

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 3 | 2026-07-09 | 2026-07-15 | Varnika Devi | Start validating supplier data | Stop manual duplicate checking | Continue supplier compliance work | Added validation and duplicate checks
2 | Sprint 3 | 2026-07-09 | 2026-07-15 | Imdad | Start testing employee and approval modules | Stop delaying integration testing | Continue backend development | Improved module testing and validation
3 | Sprint 3 | 2026-07-09 | 2026-07-15 | Varnika Devi | Start testing Purchase Order workflow early | Stop creating PO without status checks | Continue procurement workflow development | Added approval and status validations
4 | Sprint 4 | 2026-07-16 | 2026-07-22 | Imdad | Start security testing from the beginning | Stop testing only at the end | Continue API development | Added role-based access validation
5 | Sprint 4 | 2026-07-16 | 2026-07-22 | Varnika Devi | Start monitoring system activities | Stop ignoring audit log issues | Continue security improvements | Configured audit logging and monitoring
6 | Sprint 4 | 2026-07-16 | 2026-07-22 | Imdad | Start API integration testing | Stop testing modules independently | Continue integration work | Tested and fixed REST API integration
7 | Sprint 4 | 2026-07-16 | 2026-07-22 | Varnika Devi | Start deployment testing earlier | Stop last-minute deployment changes | Continue performance optimization | Fixed deployment issues and optimized performance