## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Kaveri | 2026-07-10 | Project Title:Enterprise Procurement System | 2026-07-13 | Kaveri | Logical | added Input Validation before suaving | 2026-07-03 | 9/7/2026 Closed | Registration functionality tested and working as expected.
|  |  | Our Team Task: Display Only Verified Suppliers | [6 empty] | Input validation implemented successfully.
|  |  | My Task: Supplier-Registraion | [6 empty] | Supplier details are saved correctly after validation.
Module completed and verified without any issues.
2 | Varnika Devi | 2026-07-10 | Duplicate GST Validation | 2026-07-13 | varnika-devi | Logical | Removed Duplicate Gst Numbers,Pan Numbers | 2026-07-03 | 9/7/2026 Closed | Duplicate GST validation implemented successfully and verified.
GST uniqueness check added and tested successfully.
System now prevents duplicate GST registrations as expected.
Module completed and verified without any issues.
3 | Imdad | 2026-07-10 | Documnet Verifaction | 2026-07-13 | Imdad | Logical | Implemented verification logic for GST, PAN, and License documents before supplier approval. | 2026-07-03 | 9/7/2026 Closed | Document verification completed successfully and verified through testing.
4 | Navya | 2026-07-10 | Approve or reject suppliers, display only approved suppliers, | 2026-07-13 | Navya | Logical | Fixed the approval logic to display only approved suppliers and corrected the city search functionality. | 2026-07-03 | 9/7/2026 Closed | Approval and city search functionality implemented successfully. Tested and verified with different supplier record
5 | Deepika | 2026-07-10 | Main Menu & Integration | 2026-07-13 | Deepika | Logical | Fixed menu navigation, integrated all modules successfully, and added input validation with exception handling for invalid menu selections. | 2026-07-03 | 9/7/2026 Closed | Main menu and module integration completed successfully. Application tested, all modules integrated correctly, and invalid input handled without errors.
Module 2
1 | Imdad | 2026-07-17 | Employee is able to approve their own purchase requisition. | 2026-07-18 | Imdad | Logical | Added validation to compare requester and approver IDs. | 2026-07-19 | 24/7/2026 closed | Self-approval is now restricted.
2 | Imdad | 2026-07-17 | Procurement Officer can approve before Manager approval. | 2026-07-18 | Imdad | Logical | Enforced approval hierarchy. | 2026-07-19 | 24/7/2026 closed | Correct approval sequence followed.
3 | Imdad | 2026-07-17 | Employee was made a same product request again and again | 2026-07-18 | Imdad | Logical | Duplicate Request Ignored | 2026-07-19 | 24/7/2026 closed | Employee cannot raise request again and again within that month...
4 | Varnika Devi | 2026-07-18 | Duplicate supplier registration is allowed with the same GST number. | 2026-07-19 | Varnika | Logical | Added duplicate GST validation. | 2026-07-19 | 24/7/2026 closed | Duplicate suppliers prevented.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others

## Defects (1)
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Kaveri | 2026-07-10 | Project Title:Enterprise Procurement System | System accepts empty fields or invalid supplier details during registration. | Kaveri | Logical | added Input Validation before suaving | 2026-07-03 | 9/7/2026 Closed | Registration functionality tested and working as expected.
|  |  | Our Team Task: Display Only Verified Suppliers | [6 empty] | Input validation implemented successfully.
|  |  | My Task: Supplier-Registraion | [6 empty] | Supplier details are saved correctly after validation.
Module completed and verified without any issues.
2 | Varnika Devi | 2026-07-10 | Duplicate GST Validation | System allows duplicate GST numbers during supplier registration. | varnika-devi | Logical | Removed Duplicate Gst Numbers,Pan Numbers | 2026-07-03 | 9/7/2026 Closed | Duplicate GST validation implemented successfully and verified.
GST uniqueness check added and tested successfully.
System now prevents duplicate GST registrations as expected.
Module completed and verified without any issues.
3 | Imdad | 2026-07-10 | Documnet Verifaction | Supplier documents are not verified before approval. | Imdad | Logical | Implemented verification logic for GST, PAN, and License documents before supplier approval. | 2026-07-03 | 9/7/2026 Closed | Document verification completed successfully and verified through testing.
4 | Navya | 2026-07-10 | Approve or reject suppliers, display only approved suppliers, | Approved suppliers are not displayed correctly / Search by city returns incorrect results. | Navya | Logical | Fixed the approval logic to display only approved suppliers and corrected the city search functionality. | 2026-07-03 | 9/7/2026 Closed | Approval and city search functionality implemented successfully. Tested and verified with different supplier record
5 | Deepika | 2026-07-10 | Main Menu & Integration | Main menu navigation does not open the correct module / Application crashes for invalid menu input. | Deepika | Logical | Fixed menu navigation, integrated all modules successfully, and added input validation with exception handling for invalid menu selections. | 2026-07-03 | 9/7/2026 Closed | Main menu and module integration completed successfully. Application tested, all modules integrated correctly, and invalid input handled without errors.
6 | Varnika Devi | 2026-07-16 | Supplier Registration | System accepts empty fields or invalid supplier details during registration. | varnika-devi | Logical | added Input Validation using @NotBlank | 2026-07-16 | closed | Suppplier registration validation implemented successfully
7 | Varnika Devi | 2026-07-17 | Supplier Registration | Duplicate GST numbers allowed during supplier registration | varnika-devi | Logical | Added GST uniqueness validation in service layer | 2026-07-17 | closed | Duplicate GST validation implemented successfully and verified.
8 | Varnika Devi | 2026-07-18 | Supplier Compliance | Expired compliance documents accepted by the system | varnika-devi | Logical | Added expiry date validation check | 2026-07-18 | closed | Expired compliance documents are now rejected
9 | Varnika Devi | 2026-07-19 | Approval Hierarchy | Duplicate approval levels created for same department | varnika-devi | Logical | Added duplicate approval level validation | 2026-07-19 | closed | Approval Hierarchy is now maintained correctly
10 | Varnika Devi | 2026-07-24 | Supplier Performance | Rating value greater than 5 accepted | varnika-devi | Logical | Added rating range validation(0-5) | 2026-07-24 | closed | Supplier rating are validated successfully
11 | Varnika Devi | 2026-07-25 | Supplier Performance | Performance record created for non existing supplier | varnika-devi | Logical | Added supplier existence validation | 2026-07-26 | closed | Supplier exixtence is verified before performance record creation
12 | Imdad | 2026-07-17 | Employee is able to approve their own Purchase Requeistion | 2026-07-18 | Imdad | Logical | Added Validation to compare requester and approve IDs. | 2026-07-18 | closed | self approval is now restricted.
13 | Imdad | 2026-07-19 | Procurement Officer can approve before Manager approval. | 2026-07-19 | Imdad | Logical | Enforced approvel hierarchy. | 2026-07-21 | closed | correct approval sequence is followed
14 | Imdad | 2026-07-23 | Intially Employee was Made a request of same product again and again.its like duplicate request allowed Intially | 2026-07-23 | Imdad | Logical | Duplicate Request Ignored | 2026-07-24 | closed | Employee cannot raise request of same product again and again...
15 | Imdad | 2026-08-03 | Purchase order created without approved requisition | sprint 3 | Imdad | Logical | Added validation to allow PO creation only for approved requisitions |  | closed | Purchase order creation is now restricted to approved requisitions and tested successfully
16 | Imdad | 2026-08-03 | Same Purchase Order generated multiple times for one request | sprint 3 | Imdad | Logical | Added duplicate PO check before saving |  | closed | Duplicate purchase orders are prevented and unique PO generation is verified
17 | Varnika Devi | 2026-08-04 | Supplier can accept already rejected Purchase Order | sprint 3 | varnika-devi | Logical | Added status validation before acceptance |  | closed | Rejected purchase orders can no longer be accepted by suppliers
18 | Varnika Devi | 2026-08-04 | Payment processed before goods received | sprint 4 | Imdad | Logical | Added GOODS_RECEIVED status verification in Payment Service |  | closed | Payment is processed only after goods receipt confirmation and verified successfully
19 | Imdad | 2026-08-05 | Purchase order status accepts invalid values | sprint 4 | Imdad | Logical | Added status whitelist validation(Packed,shipped,delivered) |  | closed | Invalid purchase order statuses are blocked and accepted values are validated
20 | Varnika Devi | 2026-08-05 | Employee registration accepts duplicate email IDs | sprint 2 | varnika-devi | Logical | Added unique email validation |  | closed | Duplicate employee email IDs are prevented and uniqueness is verified
21 | Imdad | 2026-08-06 | Employee created without mandatory fields | sprint 2 | Imdad | Logical | Added @NotBlank and @NotNull validations |  | closed | Mandatory employee fields are validated successfully before record creation
22 | Imdad | 2026-08-06 | Employee role entered with invalid value | sprint 2 | Imdad | Logical | Added role validation(Employee,manager,procurement_officer) |  | closed | Invalid employee roles are rejected and role validation is working correctly
23 | Varnika Devi | 2026-08-06 | Supplier registration allows weak password | sprint 2 | varnika-devi | Logical | Added password strength validation |  | closed | Weak passwords are rejected and password policy enforcement is verified
24 | Imdad | 2026-08-06 | Inactive supplier displayed in approved supplier list | sprint 3 | Imdad | Logical | Filtered suppliers by ACTIVE status |  | closed | Inactive suppliers are excluded from approved supplier listings successfully
25 | Varnika Devi | 2026-08-06 | Supplier approval possible without document verification | sprint 3 | varnika-devi | Logical | Added compliance verification before approval |  | closed | Supplier approval now requires successfully document verification and compliance checks
26 | Varnika Devi | 2026-08-15 | User with invalid role could access restricted features | sprint 4 | varnika-devi | Security | Added role based acess validation |  | closed | Role based access control was implemented successfully
27 | Varnika Devi | 2026-08-15 | Unauthorized user could access admin endpoints | sprint 4 | varnika-devi | Security | Added authorization checks for admin APIs |  | closed | Unauthorized admin access was prevented successfully
28 | Varnika Devi | 2026-08-15 | Audit logs were not recorded for important user actions | sprint 4 | varnika-devi | Logical | Implemented audit logging for critical operations |  | closed | Audit logging was implemented for critical user actions
29 | Varnika Devi | 2026-08-16 | Incorrect login attempts were not recorded for important user actions | sprint 4 | varnika-devi | Security | Added login activity monitoring and logging |  | closed | Login activities are now properly monitored and recorded
30 | Varnika Devi | 2026-08-16 | REST API returned incorrect response for invalid requests | sprint 4 | varnika-devi | API | Added request validation and proper error responses |  | closed | API validation and error handling were corrected successfully
31 | Varnika Devi | 2026-08-16 | API endpoint allowed access without authentication | sprint 4 | varnika-devi | Security | Added authentication checks to protected endpoints |  | closed | Authentication was added to all protected API endpoints
32 | Varnika Devi | 2026-08-16 | API integration failed due to incorrect request format | sprint 4 | varnika-devi | Integration | Corrected request mapping and API configuration |  | closed | API request mapping was corrected and integration works properly
33 | Varnika Devi | 2026-08-16 | Application failed during deployment due to configuration issues | sprint 4 | varnika-devi | Deployment | Corrected environment and application configuration |  | closed | Deployment configuration issues were resolved successfully
34 | Varnika Devi | 2026-08-16 | Application response was slow for large data requests | sprint4 | varnika-devi | performance | Optimized database queries and API responses |  | closed | Application performance was improved through query optimization
35 | Varnika Devi | 2026-08-16 | Project documentation contained outdated API details | sprint 4 | varnika-devi | Documentation | Updated API endpoints,configuration and usage details |  | closed | Project documentation was updated with the latest API details

## Sheet2 (1)
Logical
User Interface
Maintainability
Standards
Security
API
Integration
Deployment
performance
Documentation